## Gantt Chart
Objective | Type | Duration | Notes | YearBudget | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. GO TO MARKET ACTIVITIES
1.1 Market Research & Competitive Analysis | Research | M1-M3 (3 mo) | Analyze target segments, competitors, pricing | 15000 | bar: Jan to Mar
1.2 Product Launch & Marketing Campaign | Marketing | M4-M8 (5 mo) | Brand positioning, digital campaigns, PR | 35000 | bar: Apr to Aug
2. DEVELOPMENT WORK
2.1 Core Platform Development | Engineering | M1-M6 (6 mo) | Backend services, API, database design | 80000 | bar: Jan to Jun
2.2 Frontend / UI Implementation | Engineering | M3-M7 (5 mo) | React UI, dashboards, user workflows | 45000 | bar: Mar to Jul
2.3 Testing, QA & Deployment | QA / DevOps | M7-M10 (4 mo) | Integration tests, UAT, CI/CD, staging/prod | 25000 | bar: Jul to Oct
3. OUTREACH
3.1 Community Engagement & Partnerships | Outreach | M5-M9 (5 mo) | Conferences, webinars, partner onboarding | 20000 | bar: May to Sep
3.2 Customer Pilots & Feedback Loop | Outreach | M8-M12 (5 mo) | Pilot deployments, collect feedback, iterate | 30000 | bar: Aug to Dec
TOTAL BUDGET |  |  |  | 250000
LEGEND: | Go to Market = Green | Development = Blue | Outreach = Red